## Budget
Budget Baseline
Proj: | Phase Purple Project | [8 empty] | Date: | 2021-06-09
PM: | Slade Wilson
ID | Task Name | Project Manager | Project Administrator | Project Sponsors | Project Team | Inspection/ Safety Officer | Project Architect | Construction | Labor Cost | Contingency (L) | Materials | Contingency (M) | Total
|  | 60 | 40 | 100 | 45 | 48 | 55 | 40 |  | 28.25% |  | 28.25%
Number of Hours per Stakeholder
1.1.1 | Initiation, Evaluation, and Recommendation | 7 | 5 | 5 | 0 | 0 | 6 | 0 | 1450 | 409.625 |  | 0 | 1859.625
1.1.2 | Determine project team | 8 | 5 | 2 | 8 | 0 | 0 | 0 | 1240 | 350.3 |  | 0 | 1590.3
1.1.3 | Develop project charter | 8 | 2 | 2 | 10 | 0 | 0 | 0 | 1210 | 341.825 |  | 0 | 1551.825
1.1.4 | Project team kickoff meeting | 7 | 2 | 5 | 7 | 1 | 1 | 0 | 1418 | 400.585 |  | 0 | 1818.585
1.1.5 | Submission of project charter | 4 | 3 | 0 | 10 | 1 | 0 | 0 | 858 | 242.385 |  | 0 | 1100.385
1.1.6 | Project sponsor review | 8 | 5 | 9 | 4 | 0 | 0 | 0 | 1760 | 497.2 |  | 0 | 2257.2
1.1.7 | Project charter signed | 8 | 5 | 3 | 8 | 1 | 0 | 0 | 1388 | 392.11 |  | 0 | 1780.11
1.2.1 | Second meeting | 8 | 7 | 5 | 8 | 7 | 4 | 0 | 2176 | 614.72 |  | 0 | 2790.72
1.2.2 | Develop project plan | 7 | 1 | 7 | 9 | 5 | 9 | 0 | 2300 | 649.75 |  | 0 | 2949.75
1.2.3 | Find contractors | 8 | 5 | 0 | 8 | 0 | 8 | 0 | 1480 | 418.1 |  | 0 | 1898.1
1.2.4 | Work area map and construction | 3 | 3 | 0 | 9 | 3 | 9 | 35 | 2744 | 1022.18 | 105000 | 29662.5 | 138428.68
1.2.5 | Submit project plan | 5 | 2 | 2 | 5 | 0 | 0 | 0 | 805 | 227.4125 |  | 0 | 1032.4125
1.2.6 | Project plan approval | 5 | 2 | 5 | 5 | 0 | 0 | 0 | 1105 | 312.1625 |  | 0 | 1417.1625
1.3.1 | Third meeting | 7 | 4 | 1 | 8 | 1 | 2 | 2 | 1278 | 361.035 |  | 0 | 1639.035
1.3.2 | Construct administrative area | 8 | 8 | 0 | 10 | 8 | 20 | 40 | 4334 | 1224.355 | 97386 | 27511.545 | 130455.9
1.3.3 | Purchase new equipment | 5 | 8 | 2 | 10 | 12 | 8 | 8 | 2606 | 736.195 | 63537 | 17949.2025 | 84828.3975 | Post-Delay AC | 2 groups w/ covid | Extra crew + 40%
1.3.4 | Install new workstations and equipment | 8 | 10 | 0 | 12 | 25 | 20 | 80 | 6920 | 2201.9 | 13250 | 3743.125 | 26115.025 | 32135.025 | 4300 | 6020
1.3.5 | Organize | 5 | 6 | 0 | 8 | 0 | 10 | 14 | 2010 | 567.825 |  | 0 | 2577.825
1.3.6 | Testing phase | 3 | 3 | 0 | 5 | 7 | 7 | 7 | 1526 | 431.095 |  | 0 | 1957.095
1.3.7 | User training | 0 | 0 | 0 | 9 | 10 | 0 | 0 | 885 | 250.0125 |  | 0 | 1135.0125
1.4.1 | Project fourth meeting | 9 | 5 | 5 | 12 | 6 | 6 | 0 | 2398 | 677.435 |  | 0 | 3075.435
1.4.2 | Fire marshall approval | 6 | 7 | 0 | 1 | 8 | 0 | 0 | 1069 | 301.9925 |  | 0 | 1370.9925
1.4.3 | Risk management | 10 | 7 | 0 | 15 | 7 | 7 | 0 | 2276 | 642.97 |  | 0 | 2918.97
1.5.1 | Check project deliverables | 8 | 15 | 5 | 10 | 10 | 4 | 0 | 2730 | 771.225 | 50000 | 14125 | 67626.225 | *$50,000 for Licensing Costs / Inspection Fees
1.5.2 | Document lessons learned | 8 | 15 | 5 | 15 | 5 | 5 | 5 | 2970 | 839.025 |  | 0 | 3809.025
1.5.3 | Update files/records | 12 | 8 | 2 | 10 | 8 | 6 | 2 | 2484 | 701.73 |  | 0 | 3185.73
1.5.4 | Approval to close project | 6 | 3 | 2 | 4 | 0 | 6 | 3 | 1310 | 370.075 |  | 0 | 1680.075
1.5.5 | Close contractors | 8 | 8 | 0 | 0 | 8 | 8 | 15 | 2224 | 628.28 |  | 0 | 2852.28
1.5.6 | Submit closing reports | 8 | 8 | 9 | 7 | 8 | 8 | 8 | 3159 | 1139.4175 |  | 0 | 4298.4175
| Totals | 197 | 162 | 76 | 227 | 141 | 154 | 219 | 60113 | 17722.9225 | 329173 | 92991.3725 | 500000.295

## Schedule
Baseline schedule
Priject : | Phase purple
PM: | Slade Wilson
| WBS | Plan dates
ID | Task Name | Duration (days) | Start date | Finish date | Constraints
1.1.1 | Initiation, Evaluation, and Recommendation | 3 | 2021-06-01 | 2021-06-03 | Must start on 6/1
1.1.2 | Determining Project team | 2 | 2021-06-04 | 2021-06-05 | Will work into the weekend dates
1.1.3 | Develop Project Charter | 15 | 2021-06-06 | 2021-06-22 | Cannot start until 1.1.2 is complete
1.1.4 | Project Team Kickoff meeting | 1 | 2021-06-23 | 2021-06-23 | Cannot start until 1.1.3 is complete
1.1.5 | Submit Project Charter | 1 | 2021-06-24 | 2021-06-24 | Cannot be submitted until all team members approved and until 1.1.4 is complete
1.1.6 | Project Sponsor Reviews | 4 | 2021-06-25 | 2021-06-28 | Reviewed by all sponsors. Can sart only after 1.1.5
1.1.7 | Project Charter Signed | 1 | 2021-06-29 | 2021-06-29 | Stakeholders must be present (can start only after 1.1.6)
1.2.1 | Project Second Meeting | 1 | 2021-06-30 | 2021-06-30 | Cannot start until charter is signed
1.2.2 | Develop Project Plan | 5 | 2021-06-30 | 2021-07-04 | Cannot start until stakeholders sign approval (Half Staff - Holiday)
1.2.3 | Find Contractors | 7 | 2021-07-05 | 2021-07-11 | Cannot start until plan is approved. Must receive 3 quotes on all subjects
1.2.4 | Work Area Map | 10 | 2021-07-12 | 2021-07-21 | Cannot start until after second meeting
1.2.5 | Submit Project Plan | 1 | 2021-07-12 | 2021-07-12 | Cannot submit until second meeting
1.2.6 | Project Plan Approval | 2 | 2021-07-13 | 2021-07-14 | Cannot be approved until all sponsors and stakeholders are involved
1.3.1 | Project Third meeting | 1 | 2021-07-15 | 2021-07-15 | Cannot start third meeting until feedback of stakeholderes
1.3.2 | Construct Administrative Area | 7 | 2021-07-16 | 2021-07-22 | Will need map completed before construction (cannot start until 1.2.4 to 1.3.1 is finalized)
1.3.3 | Purchase New Equipmenmt | 44 | 2021-07-16 | 2021-08-28 | Must start after project plan approval *DELIVERY DELAYED 14 DAYS*
1.3.4 | Install New Equipmnet | 5 | 2021-08-29 | 2021-09-03 | Must wait for all equipment to be delivered
1.3.5 | Organize | 4 | 2021-09-04 | 2021-09-08 | Organize after all equipment arrives (can only start after 1.3.4)
1.3.6 | Testing Phase | 3 | 2021-09-04 | 2021-09-07 | Will begin with first fully installed machine and do one at a time.
1.3.7 | User Training | 4 | 2021-09-04 | 2021-09-08 | Saturday will be for anyone who missed the training
1.4.1 | Project Fourth Meeting | 1 | 2021-09-08 | 2021-09-09 | Cannot occur until testing is complete
1.4.2 | Fire Marshal Approval | 1 | 2021-09-10 | 2021-09-11 | Cannot set up appointment until map, equipment and admin area is complete
1.4.3 | Risk Management | 5 | 2021-09-12 | 2021-09-17 | Cannot be assessed until fire marshals approval
1.5.1 | Check Project Deliverabales | 2 | 2021-09-18 | 2021-09-20 | Must include all of project team feedback
1.5.2 | Document Lessons Learned | 2 | 2021-09-18 | 2021-09-20 | Following US Holiday (completed after 1.5.2)_
1.5.3 | Update Files / Records | 2 | 2021-09-18 | 2021-09-20 | Cannot start until admin area is complete (Half Staff - Holiday)
1.5.4 | Approval to Close Project | 2 | 2021-09-21 | 2021-09-23 | Will need approval from all members, stakeholders and sponsors (start after 1.5.3)
1.5.5 | Close Contractors | 1 | 2021-09-24 | 2021-09-25 | Will need accounting approval to payout contractors (cannot start until 1.5.4)
1.5.6 | Submit Closing Reports | 1 | 2021-09-26 | 2021-09-27 | Everything will need to be completed to close project
138

## Gantt
Gantt Chart
| Proj: | Team Purple Phase Racing | 2021-06-14
| PM: | Slade Wilson
Days
ID | Task |  | Dur | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114
1.1.1 | Initiation, Evaluation, and Recommendation |  | 3
1.1.2 | Determining Project Team |  | 2
1.1.3 | Develop Project Charter |  | 15
1.1.4 | Project Team Kickoff Meeting |  | 1
1.1.5 | Submit Project Charter |  | 1
1.1.6 | Project Sponsor Reviews |  | 4
1.1.7 | Project Charter Signed |  | 1
1.2.1 | Project Second Meeting |  | 1
1.2.2 | Develop Project Plan |  | 5
1.2.3 | Find Contractors |  | 7
1.2.4 | Work Area Map |  | 10
1.2.5 | Submit Project Plan |  | 1
1.2.6 | Project Plan Approval |  | 2
1.3.1 | Project Third Meeting |  | 1
1.3.2 | Construct Administrative Area |  | 7
1.3.3 | Purchase New Equipment |  | 44
1.3.4 | Install New Equipment |  | 5
1.3.5 | Organize |  | 4
1.3.6 | Testing Phase |  | 3
1.3.7 | User Training |  | 4
1.4.1 | Project Fourth Meeting |  | 1
1.4.2 | Fire Marshal Approval |  | 1
1.4.3 | Risk Management |  | 5
1.5.1 | Check Project Deliverables |  | 2
1.5.2 | Document Lessons Learned |  | 2
1.5.3 | Update Files/Records |  | 2
1.5.4 | Approval to Close Project |  | 2
1.5.5 | Close Contractors |  | 1
1.5.6 | Submit Closing Reports |  | 1

## Network
[23 empty] | 34 | 1.2.1 | 35 |  |  |  | 48 | 1.2.4 | 58
[23 empty] | 10 | Second Meeting |  |  |  |  | 4 | Work Area Map
[23 empty] | 44 | 1 | 45 |  |  |  | 52 | 10 | 62
|  | 0 | 1.1.1 | 3 | 4 | 1.1.2 | 6 | 7 | 1.1.3 | 22 | 23 | 1.1.4 | 24 | 25 | 1.1.5 | 26 | 27 | 1.1.6 | 31 | 32 | 1.1.7 | 33 |  |  |  | 40 | 1.2.3 | 47 | [6 empty] | 59 | 1.3.1 | 60 | 61 | 1.3.2 | 68 | [6 empty] | 112 | 1.3.5 | 116
|  | 13 | Initiation/Evaluation/Recommendation |  | 12 | Determine Team |  | 11 | Develop Charter |  | 10 | Kickoff Meeting |  | 9 | Submit Charter |  | 8 | Sponsor Reviews |  | 7 | Charter Signed |  |  |  |  | 5 | Find Contractors | [7 empty] | 3 | Third Meeting |  | 44 | Construct Admin. Area | [7 empty] | 0 | Organize
|  | 13 | 3 | 16 | 16 | 2 | 18 | 18 | 15 | 33 | 33 | 1 | 34 | 34 | 1 | 35 | 35 | 4 | 39 | 39 | 1 | 40 |  |  |  | 45 | 7 | 52 | [6 empty] | 62 | 1 | 63 | 105 | 7 | 112 | [6 empty] | 112 | 4 | 116 | [9 empty] | 126 | 1.5.1 | 128
[23 empty] | 34 | 1.2.2 | 39 |  |  |  | 48 | 1.2.5 | 49 | 50 | 1.2.6 | 52 | [6 empty] | 61 | 1.3.3 | 105 | 106 | 1.3.4 | 111 | [6 empty] | 118 | 1.4.2 | 119 | 120 | 1.4.3 | 125 | 1 | Check Project Deliverables |  | 129 | 1.5.4 | 131 | 132 | 1.5.5 | 133 | 134 | 1.5.6 | 135
[23 empty] | 6 | Project Plan |  |  |  |  | 11 | Submit Project Plan |  | 10 | Project Plan Approval | [7 empty] | 2 | Purchase New Equip. |  | 1 | Install New Equip. | [7 empty] | 3 | Fire Marshal Approval |  | 2 | Risk Management |  | 127 | 2 | 129 | 2 | Approval to Close |  | 1 | Close Contractors |  | 0 | Submit Closing Reports
[23 empty] | 40 | 5 | 45 |  |  |  | 59 | 1 | 60 | 60 | 2 | 62 | [6 empty] | 63 | 44 | 107 | 107 | 5 | 112 | [6 empty] | 121 | 1 | 122 | 122 | 5 | 127 |  |  |  | 131 | 2 | 133 | 133 | 1 | 134 | 134 | 1 | 135
[47 empty] | 112 | 1.3.6 | 115 | 116 | 1.4.1 | 117 | [6 empty] | 126 | 1.5.2 | 128
Critical Path Defined: |  |  | Series of interdependent activities of a project connected end-to-end, which determines the shortest total length of the project. | [43 empty] | 1 | Testing Phase |  | 4 | Fourth Meeting | [7 empty] | 1 | Document Lessons Learned
[47 empty] | 113 | 3 | 116 | 120 | 1 | 121 | [6 empty] | 127 | 2 | 129
Phase Purple's Critical Path: |  |  |  | 1.1.1-1.1.2-1.1.3-1.1.4-1.1.5-1.1.6-1.1.7-1.2.2-1.2.3-1.2.4-1.3.1-1.3.2-1.3.3-1.3.4-1.3.5-1.3.7-1.4.1-1.4.2-1.4.3-1.5.1-1.5.3-1.5.4-1.5.5-1.5.6
[47 empty] | 112 | 1.3.7 | 116 | [9 empty] | 126 | 1.5.3 | 128
[47 empty] | 4 | User Training | [10 empty] | 3 | Update Files/Records
|  |  | KEY | [43 empty] | 116 | 4 | 120 | [9 empty] | 129 | 2 | 131
| Early Start |  | ID | Early Finish
| Float |  | Activity Name
| Late Start |  | Duration | Late Finish
Lag 8
Lag 5
Start
End
Lag 28
Lag 1
Lag 1

## EV Plan
WP | Task | Dur | $ Labor | $ Material | PV | EV Measure | Wk Ending: | 2021-05-21 | 2021-05-28 | 2021-06-04 | 2021-06-11 | 2021-06-18 | 2021-06-25 | 2021-07-02 | 2021-07-09 | 2021-07-16 | 2021-07-23 | 2021-07-30 | 2021-08-06 | 2021-08-13 | 2021-08-20 | 2021-08-27 | 2021-09-03 | 2021-09-10 | 2021-09-17 | 2021-09-24 | Totals
1.1.1 | Initiation, Evaluation, and Recommendation | 3 | 1859.625 | 0 | 1859.625 | 100 |  |  |  | 1859.625 | [16 empty] | 1859.625 | PV | Variance Analysis Report
[10 empty] | 1859.625 | [16 empty] | 1859.625 | AC | Proj | Phase Purple |  | Data Date:
[10 empty] | 1859.625 | [16 empty] | 1859.625 | EV | PM: | Slade Wilson |  | Date:
1.1.2 | Determining Project Team | 2 | 1590.3 | 0 | 1590.3 | 50/50 |  |  |  | 795.15 | 795.15 | [15 empty] | 1590.3 | PV
[10 empty] | 795.15 | 795.15 | [15 empty] | 1590.3 | AC | Project EVM Data |  | Analysis and Recommendations
[10 empty] | 795.15 | 795.15 | [15 empty] | 1590.3 | EV | SV = | 0 | Progress Since Last Report and Project Status:
1.1.3 | Develop Project Charter | 15 | 1551.825 | 0 | 1551.825 | 50/50 | [5 empty] | 775.9125 | 775.9125 | [13 empty] | 1551.825 | PV | CV = | -6020 | Project has been completed and closed.
[12 empty] | 775.9125 | 775.9125 | [13 empty] | 1551.825 | AC | Planned % Complete = | 98.81%
[12 empty] | 775.9125 | 775.9125 | [13 empty] | 1551.825 | EV | PCB = | 100%
1.1.4 | Project Team Kickoff Meeting | 1 | 1818.585 | 0 | 1818.585 | 100 | [6 empty] | 1818.585 | [13 empty] | 1818.585 | PV | PCC = | 100%
[13 empty] | 1818.585 | [13 empty] | 1818.585 | AC | BAC = | 500000.295
[13 empty] | 1818.585 | [13 empty] | 1818.585 | EV | EACf = | 506020.295
1.1.5 | Submit Project Charter | 1 | 1100.385 | 0 | 1100.385 | 100 | [6 empty] | 1100.385 | [13 empty] | 1100.385 | PV
[13 empty] | 1100.385 | [13 empty] | 1100.385 | AC |  |  | Project Trends
[13 empty] | 1100.385 | [13 empty] | 1100.385 | EV |  |  | Closed.
1.1.6 | Project Sponsor Reviews | 4 | 2257.2 | 0 | 2257.2 | 50/50 | [6 empty] | 1128.6 | 1128.6 | [12 empty] | 2257.2 | PV
[13 empty] | 1128.6 | 1128.6 | [12 empty] | 2257.2 | AC
[13 empty] | 1128.6 | 1128.6 | [12 empty] | 2257.2 | EV
1.1.7 | Project Charter Signed | 1 | 1780.11 | 0 | 1780.11 | 100 | [7 empty] | 1780.11 | [12 empty] | 1780.11 | PV
[14 empty] | 1780.11 | [12 empty] | 1780.11 | AC
[14 empty] | 1780.11 | [12 empty] | 1780.11 | EV |  |  | Problems, Issues, and Planned Corrective Actions
1.2.1 | Project Second Meeting | 1 | 2790.72 | 0 | 2790.72 | 100 | [7 empty] | 2790.72 | [12 empty] | 2790.72 | PV |  |  | Shipping delays of 2 weeks on materials and supplies. Costs 20% more to get the delivery on time. - Project team and client opted to allow material delay. Project Architect and entire construction team out for 2 weeks with COVID-19 delta variant staring August 20th. Must pay them their entire salary the whole time. - Project team and client opted to hire temporary replacement team for 2 weeks since the project had already been delayed 2 weeks for materials. This doubled cost of labor for project architect and construction team + 40% due to temporary hires.
[14 empty] | 2790.72 | [12 empty] | 2790.72 | AC
[14 empty] | 2790.72 | [12 empty] | 2790.72 | EV
1.2.2 | Develop Project Plan | 5 | 2949.75 | 0 | 2949.75 | 100 | [7 empty] | 2949.75 | [12 empty] | 2949.75 | PV
[14 empty] | 2949.75 | [12 empty] | 2949.75 | AC
[14 empty] | 2949.75 | [12 empty] | 2949.75 | EV
1.2.3 | Find Contractors | 7 | 1898.1 | 0 | 1898.1 | 100 | [8 empty] | 1898.1 | [11 empty] | 1898.1 | PV
[15 empty] | 1898.1 | [11 empty] | 1898.1 | AC
[15 empty] | 1898.1 | [11 empty] | 1898.1 | EV
1.2.4 | Work Area Map and Construction | 10 | 3766.18 | 134662.5 | 138428.68 | 50/50 | [9 empty] | 69214.34 | 69214.34 | [9 empty] | 138428.68 | PV
[16 empty] | 69214.34 | 69214.34 | [9 empty] | 138428.68 | AC
[16 empty] | 69214.34 | 69214.34 | [9 empty] | 138428.68 | EV
1.2.5 | Submit Project Plan | 1 | 1032.4125 | 0 | 1032.4125 | 100 | [9 empty] | 1032.4125 | [10 empty] | 1032.4125 | PV
[16 empty] | 1032.4125 | [10 empty] | 1032.4125 | AC
[16 empty] | 1032.4125 | [10 empty] | 1032.4125 | EV
1.2.6 | Project Plan Approval | 2 | 1417.1625 | 0 | 1417.1625 | 100 | [9 empty] | 1417.1625 | [10 empty] | 1417.1625 | PV
[16 empty] | 1417.1625 | [10 empty] | 1417.1625 | AC
[16 empty] | 1417.1625 | [10 empty] | 1417.1625 | EV
1.3.1 | Project Third Meeting | 1 | 1639.035 | 0 | 1639.035 | 100 | [10 empty] | 1639.035 | [9 empty] | 1639.035 | PV
[17 empty] | 1639.035 | [9 empty] | 1639.035 | AC
[17 empty] | 1639.035 | [9 empty] | 1639.035 | EV
1.3.2 | Construct Administrative Area | 7 | 5558.355 | 124897.545 | 130455.9 | 50/50 | [10 empty] | 65227.95 | 65227.95 | [8 empty] | 130455.9 | PV
[17 empty] | 65227.95 | 65227.95 | [8 empty] | 130455.9 | AC
[17 empty] | 65227.95 | 65227.95 | [8 empty] | 130455.9 | EV
1.3.3 | Purchase New Equipment | 30 | 3342.195 | 81486.2025 | 84828.3975 | 50/50 | [12 empty] | 42414.1988 | 42414.1988 | [6 empty] | 84828.3975 | PV
[19 empty] | 42414.1988 |  |  | 42414.1988 |  |  |  |  | 84828.3975 | AC
[19 empty] | 42414.1988 |  |  | 42414.1988 |  |  |  |  | 84828.3975 | EV
1.3.4 | Install New Equipment/Workstations | 5 | 9121.9 | 16993.125 | 26115.025 | 50/50 | [13 empty] | 13057.5125 | 13057.5125 | [5 empty] | 26115.025 | PV
[22 empty] | 16067.5125 | 16067.5125 |  |  |  | 32135.025 | AC
[22 empty] | 13057.5125 | 13057.5125 |  |  |  | 26115.025 | EV
1.3.5 | Organize | 4 | 2577.825 | 0 | 2577.825 | 50/50 | [14 empty] | 1288.9125 | 1288.9125 |  |  |  |  | 2577.825 | PV
[23 empty] | 1288.9125 | 1288.9125 |  |  | 2577.825 | AC
[23 empty] | 1288.9125 | 1288.9125 |  |  | 2577.825 | EV
1.3.6 | Testing Phase | 3 | 1957.095 | 0 | 1957.095 | 100 | [14 empty] | 1957.095 | [5 empty] | 1957.095 | PV
[23 empty] | 1957.095 |  |  |  | 1957.095 | AC
[23 empty] | 1957.095 |  |  |  | 1957.095 | EV
1.3.7 | User Training | 4 | 1135.0125 | 0 | 1135.0125 | 100 | [14 empty] | 1135.0125 | [5 empty] | 1135.0125 | PV
[23 empty] | 1135.0125 |  |  |  | 1135.0125 | AC
[23 empty] | 1135.0125 |  |  |  | 1135.0125 | EV
1.4.1 | Project Fourth Meeting | 1 | 3075.435 | 0 | 3075.435 | 100 | [14 empty] | 3075.435 | [5 empty] | 3075.435 | PV
[23 empty] | 3075.435 |  |  |  | 3075.435 | AC
[23 empty] | 3075.435 |  |  |  | 3075.435 | EV
1.4.2 | Fire Marshal Approval | 1 | 1370.9925 | 0 | 1370.9925 | 100 | [15 empty] | 1370.9925 |  |  |  |  | 1370.9925 | PV
[24 empty] | 1370.9925 |  |  | 1370.9925 | AC
[24 empty] | 1370.9925 |  |  | 1370.9925 | EV
1.4.3 | Risk Management | 5 | 2918.97 | 0 | 2918.97 | 50/50 | [15 empty] | 1459.485 | 1459.485 |  |  |  | 2918.97 | PV
[24 empty] | 1459.485 | 1459.485 |  | 2918.97 | AC
[24 empty] | 1459.485 | 1459.485 |  | 2918.97 | EV
1.5.1 | Check Project Deliverables | 2 | 3501.225 | 64125 | 67626.225 | 100 | [16 empty] | 67626.225 |  |  |  | 67626.225 | PV
[25 empty] | 67626.225 |  | 67626.225 | AC
[25 empty] | 67626.225 |  | 67626.225 | EV
1.5.2 | Document Lessons Learned | 2 | 3809.025 | 0 | 3809.025 | 100 | [16 empty] | 3809.025 |  |  |  | 3809.025 | PV
[25 empty] | 3809.025 |  | 3809.025 | AC
[25 empty] | 3809.025 |  | 3809.025 | EV
1.5.3 | Update Files/Records | 2 | 3185.73 | 0 | 3185.73 | 100 | [16 empty] | 3185.73 |  |  |  | 3185.73 | PV
[25 empty] | 3185.73 |  | 3185.73 | AC
[25 empty] | 3185.73 |  | 3185.73 | EV
1.5.4 | Approval To Close Project | 2 | 1680.075 | 0 | 1680.075 | 100 | [16 empty] | 1680.075 |  |  |  | 1680.075 | PV
[25 empty] | 1680.075 |  | 1680.075 | AC
[25 empty] | 1680.075 |  | 1680.075 | EV
1.5.5 | Close Contractors | 1 | 2852.28 | 0 | 2852.28 | 100 | [17 empty] | 2852.28 |  |  | 2852.28 | PV
[26 empty] | 2852.28 | 2852.28 | AC
[26 empty] | 2852.28 | 2852.28 | EV
1.5.6 | Submit Closing Reports | 1 | 4298.4175 | 0 | 4298.4175 | 100 | [17 empty] | 4298.4175 |  |  | 4298.4175 | PV
[26 empty] | 4298.4175 | 4298.4175 | AC
[26 empty] | 4298.4175 | 4298.4175 | EV
[7 empty] | PV | 0 |  | 2654.775 | 795.15 | 775.9125 | 4823.4825 | 8649.18 | 1898.1 | 71663.915 | 136081.325 | 65227.95 | 42414.1988 | 55471.7113 | 20513.9675 | 4119.39 | 77760.54 | 7150.6975 | 0 | 0
[7 empty] | Cumulative PV | 0 |  | 2654.775 | 3449.925 | 4225.8375 | 9049.32 | 17698.5 | 19596.6 | 91260.515 | 227341.84 | 292569.79 | 334983.9888 | 390455.7 | 410969.6675 | 415089.0575 | 492849.5975 | 500000.295 | 500000.295 | 500000.295
|  | SV = | 0 |  |  |  | AC | 0 |  | 2654.775 | 795.15 | 775.9125 | 4823.4825 | 8649.18 | 1898.1 | 71663.915 | 136081.325 | 65227.95 | 42414.1988 | 0 | 0 | 58481.7113 | 23523.9675 | 4119.39 | 77760.54 | 7150.6975
|  | CV = | -6020 |  |  |  | Cumulative AC | 0 |  | 2654.775 | 3449.925 | 4225.8375 | 9049.32 | 17698.5 | 19596.6 | 91260.515 | 227341.84 | 292569.79 | 334983.9888 | 334983.9888 | 334983.9888 | 393465.7 | 416989.6675 | 421109.0575 | 498869.5975 | 506020.295
|  | Planned % Complete = | 98.81% |  |  |  | EV | 0 |  | 2654.775 | 795.15 | 775.9125 | 4823.4825 | 8649.18 | 1898.1 | 71663.915 | 136081.325 | 65227.95 | 42414.1988 | 0 | 0 | 55471.7113 | 20513.9675 | 4119.39 | 77760.54 | 7150.6975
|  | PCB = | 100% |  |  |  | Cumulative EV | 0 |  | 2654.775 | 3449.925 | 4225.8375 | 9049.32 | 17698.5 | 19596.6 | 91260.515 | 227341.84 | 292569.79 | 334983.9888 | 334983.9888 | 334983.9888 | 390455.7 | 410969.6675 | 415089.0575 | 492849.5975 | 500000.295
|  | PCC = | 100% |  |  | Indicators: | SPI | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.85793 | 0.81511 | 0.94066 | 0.83386 | 0.83018 | 0.9857 | 1
|  | EACf = | 506020.295 |  |  |  | CPI | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.99235 | 0.98556 | 0.9857 | 0.98793 | 0.9881